## Sheet1
Week | Day | Final Project | Jacob | Zuhaib | Suhayb | All
5 | 2026-06-15 | FP3 | Homepage, UI, and CSS | PHP planning | Database planning | Project planning, UX design, and code structure
6 | 2026-06-22 | FP4 | Create Classes and Students pages | Database connection | Create database tables | Connect project structure and test integration
7 | 2026-06-29 | FP5 | Design Student forms | Process form submissions | Create Students and Classes database tables | Test class and student management
8 | 2026-07-06 | FP6 | Create Assignment pages | Implement assignment logic | Create Assignment database tables | Test assignment management
9 | 2026-07-13 | FP7 | Create Submission page | Implement submission logic | Create Submission database table | Test student submission workflow
10 | 2026-07-20 | FP8 | Create Feedback page | Implement feedback logic | Create Feedback database | Test feedback system
11 | 2026-07-27 | FP9 | Improve UI | Implement resubmission logic | Update database structure | Full system integration and testing
12 | 2026-08-03 | FP10 | Final UI polishing | Bug fixes | Final database testing | Final integration, presentation preparation, and demo
13 | 2026-08-10 | FP-Final
FP 3 Scope
1. How is your website going to look like? Roles (Student, Parent, Instructor, Admin)? Actions?
2.How is the code structure / repo structure going to look like?
3. Weekly plan to meet the requirements of the project