## Sheet1
Week | Day | Final Project | Jacob | Zuhaib | Suhayb | All
5 | 2026-06-15 | FP3 | Homepage, UI, and CSS | PHP planning | Database planning | Project planning, UX design, and code structure
6 | 2026-06-22 | FP4 | Create Classes and Students pages | Database connection | Create database tables | Connect project structure and test integration
7 | 2026-06-29 | FP5 | Build Students page UI | Connect Students page to PHP/database | Create Students table and relationships | Student workflow testing
8 | 2026-07-06 | FP6 | Build Assignments page UI | Connect Assignments page to PHP/ database | Create Assignment database tables | Test assignment management
9 | 2026-07-13 | FP7 | Build Rubrics page UI | Connect Rubrics page to PHP and database | Design rubric logic and sample rubrics | Assignment workflow testing
10 | 2026-07-20 | FP8 | Build Submissions and Feedback UI | Connect Submissions and Feedback to PHP/database | Create submission workflow and AI feedback research | Rubric workflow testing
11 | 2026-07-27 | FP9 | UI polish and responsiveness | Bug fixes and feature integration | Database testing, AI testing, documentation | Submission and feedback testing
12 | 2026-08-03 | FP10 | Final UI polishing | Final backend testing and deployment | Final database testing | Final integration, presentation preparation, and demo
13 | 2026-08-10 | FP-Final
FP 3 Scope
1. How is your website going to look like? Roles (Student, Parent, Instructor, Admin)? Actions?
2.How is the code structure / repo structure going to look like?
3. Weekly plan to meet the requirements of the project