## Sheet1
Week | Day | Final Project | Jacob | Zuhaib | Suhayb | All
5 | 2026-06-15 | FP3 | Homepage, UI, and CSS | Planning for assiangments page | Database planning | Project planning, UX design, and code structure
6 | 2026-06-22 | FP4 | Classes module: UI, PHP, MySQL planning | Assignments module: UI, PHP, MySQL planning | Rubrics module: UI, PHP, MySQL planning | Connect project structure and test integration
7 | 2026-06-29 | FP5 | Build Classes full-stack: page, form, table, database insert/display | Build Assignments full-stack: page, form, table, database insert/display | Build Rubrics full-stack: page, form, table, database insert/display | Student workflow testing
8 | 2026-07-06 | FP6 | Build Students full-stack: page, form, table, database insert/display, Add edit/delete for Classes and Students | Build Students full-stack: page, form, table, database insert/display, Add edit/delete for Classes and Students | Build Feedback/Grades full-stack: rubric scoring and feedback display | Test assignment management
9 | 2026-07-13 | FP7 | Improve Classes/Students validation and UI | Add edit/delete for Assignments and Submissions | Add edit/delete for Rubrics and Feedback/Grades | Assignment workflow testing
10 | 2026-07-20 | FP8 | Add or modifty new Classes/Students validation and UI | Improve Assignments/Submissions validation and UI | Improve Rubrics/Feedback/Grades validation and UI | Rubric workflow testing
11 | 2026-07-27 | FP9 | Polish Classes/Students and test | Polish Assignments/Submissions and test | Polish Rubrics/Feedback/Grades and test | Submission and feedback testing
12 | 2026-08-03 | FP10 | Final demo prep for Classes/Students | Final demo prep for Assignments/Submissions | Final demo prep for Rubrics/Feedback | Final integration, presentation preparation, and demo
13 | 2026-08-10 | FP-Final
FP 3 Scope
| 1. How is your website going to look like? Roles (Student, Parent, Instructor, Admin)? Actions? |  |  | Parent, Instructor, Admin)? Actions? | Our website will be a clean web-based Assignment Grader System with a homepage and navigation pages for Classes, Students, Assignments, Rubrics, Submissions, and Feedback/Grades.
| 2.How is the code structure / repo structure going to look like? |  |  |  | assignment-grader/ (index.php, classes.php, students.php, assignments.php, rubrics.php, submissions.php, feedback.php, db.php, css/style.css, js/script.js, includes/header.php, includes/footer.php, database/assignment_grader.sql)
3. Weekly plan to meet the requirements of the project